## P&G
Item No | Description | Unit | Quantity | Rate | Amount
BILL NO 1
PRELIMINARIES
BUILDING AGREEMENT AND PRELIMINARIES
The JBCC Series 2000 Principal Building Agreement (edition 5 July 2007) prepared by the Joint Building Contracts Committee Inc. amended as hereinafter described, shall be the agreement
The JBCC Series 2000 Preliminaries (May 2005) prepared by the Joint Building Contracts Committee Inc. amended as hereinafter described shall be deemed to be incorporated in these bills of quantities
Contractors are referred to the above-mentioned documents for the full intent and meaning of each clause thereof
These clauses are hereinafter referred to by clause number and heading only. Where standard clauses or alternatives are not entirely applicable to this contract such modifications, corrections or supplements as will apply are given under each relevant clause heading and such modifications, corrections or supplements shall take precedence notwithstanding anything contrary contained in the above-mentioned documents
Where any item is not relevant to this specific contract such item is marked N/A, signifying "not applicable"
STRUCTURE OF THIS PRELIMINARIES BILL
Section A : A recital of the headings of the individual clauses of
the aforementioned JBCC Principal Building
Agreement
Section B : A recital of the headings of the individual clauses of
the aforementioned Preliminaries document
Section C : Any special clauses to meet the particular
circumstances of the project
PREAMBLES FOR TRADES
The Model Preambles for Trades (2008 edition) as published by the Association of South African Quantity Surveyors shall be deemed to be incorporated in these bills of quantities and no claim arising from brevity of description of items fully described in the said Model Preambles for Trades will be entertained
Supplementary preambles, Projects Specification and the document titled "Standard Specifications for Municipal Civil Engineering Works" are incorporated in the Bill of Quantities. Such supplicatory Preambles and Specifications shall take precedence over provisions of the Model Preambles.
The contractor's prices for all items throughout these bills of quantities must take account of and include for all of the obligations, requirements and specifications given in the Model Preambles and in any supplementary preambles
PRICING
If option A as set out in clause B10.3.1 hereinafter is to be used for the adjustment of the preliminaries each item priced is to be allocated to one or more of the three categories "F", "T" or "V" as the case may be below such item, where:
F · An amount which shall not be varied
V · An amount which shall be varied in proportion to the contract value as compared with the contract sum
T · An amount which shall be varied in proportion to the construction period as compared to the initial construction period excluding revisions to the construction period for which the contractor is not entitled to adjustment of the contract value in terms of the agreement
SECTION A - PRINCIPAL BUILDING AGREEMENT
DEFINITIONS (A1)
36892 | Clause 1.0 - Definitions and interpretation | Item
Clause 1.0 is deemed to be amended by the addition of the following definitions and amendments:
Parties means the person or entity named in the schedule or appointed by the employer to deal with specific aspects of the works
Confidential Information means any information disclosed by that party to the receiving party prior to the conclusion of this agreement, in terms of this agreement or otherwise in connection with agreement
the Project means the Bulk Earthworks, Lateral Support and Service Relocation Works on the Sunnyside Office Development
the Tender means the invitation to prospective service providers to provide the Employer with Bulk Earthworks,Lateral Support and Service Relocation works.
1.6.1 "Hand" be inserted before the word "Delivered
1.6.3 the word "successful" be inserted before the word "transmission"
1.6.4 the word "successful" be inserted before the word "transmission"
OBJECTIVE AND PREPARATION (A2 - A14)
37257 | Clause 2.0 - Offer, acceptance and performance | Item
37622 | Clause 3.0 - Documents | Item
Clause 3.1 is deleted
Clause 3.3. is deleted and replaced with the following:
Where the employer requires the contractor to waive his lien or right of continuing possession of the works as stated in the schedule, the contractor shall do so prior to taking possession of the works. The waiver shall be according to the JBCC Waiver of Contractors Lien Form or such other form as stated in the schedule. The Contractor shall simultaneously with the signing of every selected or domestic subcontract, deliver to the Principal Agent an undertaking and cession in respect of contractors lien which shall mutatis mutandis conform to the JBCC Waiver of Contractors Lien form.
Clause 3.5 is amended by the following; Delete the word "not" in 3rd line - Sentence should read: "Formal signatories are required to render this agreement binding."
Clause 3.0 is amended by the addition of the following:
Clause 3.12 All documentation for this project to be managed and controlled with BIM 360 and the contractor is to make his own arrangements in complying with the requirements.
Clause 3.0 is amended by the addition of the following:
Clause 3.13 All documentation for the project will be issued in the English language and the contractor is to make his own arrangements for translating this documentation into a language suitable for his purposes and that of his n/s subcontractors. The contractor and his n/s subcontractors rely on such translated documents entirely at their own risk
37987 | Clause 4.0 - Design responsibility | Item
Clause 4.0 is amended by the addition of the following:
Clause 4.4 Without limiting or derogating from the employer's rights [4.2], the contractor shall
Clause 4.4.1 ensure that every n/s subcontractor, simultaneously with the signing of the relevant n/s agreement, signs (in terms of a written signing authority acceptable to the principal agent) and delivers to the employer a design, materials and workmanship warranty and undertaking (design warranty) in favour of the employer.
Clause 4.4.2 provide to the employer evidence of suitable and sufficient professional indemnity insurance for all n/s subcontractors whose subcontract involves design work other than for temporary works
Clause 4.5 Pending delivery of the design warranty [4.4.1] and the required evidence of professional indemnity insurance [4.4.2], the contractor shall, notwithstanding anything to the contrary in the agreement and without limiting or derogating from the employer's rights [4.2], be responsible for the design undertaken by the relevant n/s subcontractor
38353 | Clause 5.0 - Employer's agents | Item
Clause 5 is deemed to be amended by the addition of the following clause:
5.3.4 The Emloyer's Legal Department must be copied in any and all notices, as contemplated herein.
38718 | Clause 6.0 - Site representative | Item
Clause 6.0 is amended by the addition of the following:
Clause 6.3 The names and CV's of the contractor's proposed management team (for both day and nightshift) shall be submitted to the principal agent prior to commencement on site and, after the principal agent's agreement on the composition and competence thereof has been obtained, no changes shall be made nor shall any member of the said team be removed from the project while remaining in the employ of the contractor, without the principal agent's prior written approval. It is required to provide contactable references and the Principal Agent will conduct interviews with the proposed Site Agent, Senior Foreman and Safety Office that will be dedicated to nightshift.
39083 | Clause 7.0 - Compliance with regulations | Item
Clause 7.0 is amended by the addition of the following clauses:
Clause 7.2 The employer reserves the right to pay direct (i.e. not through the contractor) for all or any permanent connections to local or other authority services, for which provisional amounts have been included within the selected sub-contract bill section hereof. In the event of the employer paying direct for these charges, the contractor will not be entitled to a ten percent (10%) mark-up in terms of Clause 32.4. All such provisional amounts included in the contract sum will be omitted.
Clause 7.3 Without limiting the generality of the provisions of clause 7.0 of the agreement, the contractor's attention is drawn to the provisions of the Construction Regulations, 2003 issued in terms of the Occupational Health and Safety Act, 1993 in which it is specifically stated that the employer shall prepare a documented health and safety specification for the works and that the employer shall ensure that the contractor has made provision for the cost of health and safety measures during the execution of the works. The contractor shall price opposite this item for compliance with the act and the regulations and the provisions of the aforementioned health and safety specification.
The contractor shall:
1. Comply with the health and safety specification for the
works
2. Prepare and agree with the health and safety
consultant the health and safety plan for the works
3. Co-operate with the health and safety consultant in all
respects
4. Manage the compliance of all subcontractors with the
regulations and with the health and safety plan and
specification
5. Conform to the conditions contained in the employer's
health and safety specification
Clause 7.4 The contractor shall take all reasonable precautions to maintain the health and safety of persons in and about the execution of the works. Without limitation the contractor hereby:
Clause 7.4.1 acknowledges and confirms that the contract sum includes a sufficient amount for proper compliance with all applicable health & safety laws and regulations and the health and safety rules, guidelines and procedures provided for the proper maintenance of health and safety in and about the execution of works; and
Clause 7.4.2 undertakes, in and about the execution of the works, to comply with all Health and Safety requirements and with all applicable health and safety laws and regulations and rules and guidelines and procedures otherwise provided for under the agreement and shall ensure that all subcontractors, employees and others under the contractor's direction and control, likewise observe and comply with the foregoing
Clause 7.4.3 submits a health and safety plan incorporating health and safety consultant
39448 | Clause 8.0 - Works risk | Item
Clause 8.5 is amended by the following; add wording at end of the sentence "only if such making good of physical loss and repairs have been approved in writing by the employer."
39814 | Clause 9.0 - Indemnities | Item
Clause 9.2.2 is deleted
40179 | Clause 10.0 - Works insurances | Item
Clause 10.1 Delete wording joint names of the parties and replace with name of the contractor. PIC has insurance cover for its entire portfolio and does not take out insurance on a project basis.
40544 | Clause 11.0 - Liability insurances | Item
40909 | Clause 12.0 - Effecting insurances | Item
Clause 12.2. is deleted and replaced with the following:
The contractor responsible for effecting the insurances shall make available to the employer, before commencement of the construction period, documentary evidence that insurances have been effected. A copy of the insurance policies shall be provided to the other party within thirty (30) calendar days of the commencement of the construction period. Approval by the other party shall be deemed unless a reasonable objection is lodged within fourteen (14) calendar days of receipt of such policies. Where required, the contractor shall provide evidence of renewal to the other party before the expiry of the current period of insurance.
Clause 12.3 Delete first and last sentence.
Clause 12.5 is deleted
41275 | Clause 13.0 - Assignment | Item
Clause 13.1 is deemed to be amended to read as follows:
Neither the employer nor contractor shall assign or cede his rights or obligations
41640 | Clause 14.0 - Security | Item
Clause 14.8 is deleted
Clause 14.0 is amended by the addition of the following clause:
14.9 In the event that the value of the works (excluding adjustments in terms of the contract price adjustment provisions) were to increase during the course of the contract by an amount of 15% or more of the contract sum, upon written request from the principal agent, the contractor shall immediately arrange to have the construction guarantee guaranteed sum adjusted to reflect the increased contract value. The cost of obtaining the adjusted guarantee, if any, will be dealt with in terms of Clause 32.0.
EXECUTION (A15 - A23)
42005 | Clause 15.0 - Preparation for and execution of the works | Item
Clause 15.10 is added; Provide Air conditioned office accommodation for meetings suitable for 20 persons as well as additional air conditioned office space for two workstations complete with desks , internet data connection and chairs. The office accommodation is to be kept clean and fit for use at all times
Clause 15.11 is added; Transformation Imperatives and B-BBEE
Clause 15.12 is added; In the conduct of the business, the contractor undertakes to actively promote and encourage employment equity and, in particular not to discriminate against any person on the basis of race, colour, sex, religion, age, national or ethnic origin, political belief, veteran status or handicap.
Clause 15.13 is added; the contractor is to comply with the transformation agenda as contemplated by the Public Investment Corporation, which is to contribute towards strengthening South Africa's democracy through social, moral and economic imperatives. In concluding this agreement, the contractor commits to the implementation of the Public Investment Corporation transformation imperatives, in as far as possible, in the day to day operation of its business. The definitions of the imperatives below, are reflective and can be interpreted in accordance with the Broad-Based Black Economic Empowerment Act of 2013. The key elements shall include.
Clause 15.14 is added; Ownership - measuring effective ownership by black people , wherein ownership should be 51% black owned or 35% woman owned;
Clause 15.5 is added; Management Control - measuring effective control of the entitys black people as well as initiatives intended to achieve equity in the workplace which should be aimed at reaching 51% black owned;
Clause 15.6 is added; Subcontracting at least 30% of the contract value to an Emerging Micro Enterprise or Qualifying Small Enterprise;
42370 | Clause 16.0 - Access to the works | Item
42736 | Clause 17.0 - Contract instructions | Item
43101 | Clause 18.0 - Setting out of the works | Item
Clause 18.0 is amended by the addition of the following clause:
Clause 18.5 The contractor shall notify the principal agent if any encroachments of adjoining foundations, buildings, structures, pavements, boundaries, etc exist in order that the necessary arrangements may be made for the rectification of any such encroachments
Clause 18.6. is added: Where the contractor fails to comply with the requirements of clause 18 to the satisfaction of the principal agent, progressively as the structure is constructed, the principal agent shall notify the contractor to comply within seven (7) calendar days, failing which and without any further notice, the employer shall be entitled to commission other parties to do so on the contractor's behalf and at the contractor's expense. The contractor shall provide general attendance and all reasonable assistance to such parties
43466 | Clause 19.0 - Temporary works and plant | Item
43831 | Clause 20.0 - Nominated subcontractors | Item
44197 | Clause 21.0 - Selected subcontractors | Item
Clause 21.0 is deemed to be amended by the addition of the following clause:
Clause 21.3.2 is deemed to be deleted
Clause 21 is amended by the addition of the following clause:
Clause 21.11 The contractor is to satisfy himself and give notice to the principal agent to such effect that tenderers to be appointed as selected subcontractors can fulfil the provisions of clauses 21.2.1 and 21.2.2 prior to the opening of the selected subcontract tenders.
Clause 21.12 is added; Notwithstanding the provision of the contractor's general attendance in accordance with the n/s agreement, general attendance shall be deemed to include for the contractor to provide free of charge to any n/s subcontractor erected fit for use scaffolding by the contractor (owned or hired) as may reasonably be required by such n/s subcontractor for the execution of the relevant subcontract works
44562 | Clause 22.0 - Employer's direct contractors | Item
Clause 22.6. is added: The contractor shall not be entitled to any percentage, profit or discount on the value of any work executed by direct contractors but shall nevertheless allow these direct contractors to have access to the works, allocate reasonable space in the building for the storage of their materials, tools and equipment, and co-ordinate via the principal agent the work of such direct contractors as necessary, all to the satisfaction of the principal agent. The contractor shall allow the direct contractor's, to use, free of charge, hoisting and cranage by arrangement by the principal agent, ablution facilities, water and power supply on the site, and shall not in any way hinder or prevent the execution of their work
44927 | Clause 23.0 - Contractor's domestic subcontractors | Item
COMPLETION (A24 - A30)
45292 | Clause 24.0 - Practical completion | Item
Clause 24 is amended by the addition of the following clause:
24.11. Without derogating from the generality of the requirements for practical completion the following specific requirements shall apply:
24.11.1 The practical completion list of outstanding work and defects must be completed and attended to in its entirety.
24.11.2 The contractor is to state that compliance has been achieved with respect to the full scope of the works.
24.11.3 All defects noted on the quality control sheets issued by the principal agent of the employer during the currency of the contract and under cover of contract Instructions are to have been completed and attended to their entirety.
24.12 Practical completion
24.12.1 The contractor shall inspect the works to satisfy himself that the stage of completion of the works in terms of clause 24 has been achieved.
24.12 Should the contractor, in the opinion of the principal agent, not have achieved practical completion of any area of the works on the date for practical completion as stated in the schedule, the employer may, notwithstanding the contractor's on-going responsibilities under this agreement take possession and occupation of such area(s) on the basis that:-
Penalties will only reduce as defined in the penalty schedule and on practical completion being achieved, regardless of possible beneficial occupation being given to the client for direct order fit -outs. Insurance will only transfer on practical completion being the date practical completion has been achieved.
24.12.1 Such possession and occupation by the employer shall not be construed as the achievement of practical completion by the contractor or the works or any part thereof.
24.12.2 The principal agent shall notify the contractor in writing of each area of the works which shall be occupied and possessed by the employer in terms hereof
24.12.3 For the purposes of completing his responsibilities under this agreement including but not limited to achieving practical completion of the works, the contractor shall continue to have access to any area/a of the works so occupied and possessed by the employer, but subject to such reasonable terms and conditions as the employer may impose in connection with such access.
45658 | Clause 25.0 - Works completion | Item
46023 | Clause 26.0 - Final completion | Item
46388 | Clause 27.0 - Latent defects liability period | Item
Clause 27.2.2 is deleted
46753 | Clause 28.0 - Sectional completion | Item
47119 | Clause 29.0 - Revision of date for practical completion | Item
Clause 29.2.10 is deemed to be deleted
Clause 29.0 is deemed to be amended by the addition of the following clauses:
Clause 29.5 Delete "40" and replace with "20".
29.9 A revision of the date for practical completion in terms of this clause will only be considered when work on the critical path of the programme for the works is affected (clause 29.0)
29.10 No claims for a revision of the date for practical completion due to time lost on account of inclement weather shall be considered unless the number of working days actually lost on this account during any month is in excess of the allowable number of working days lost for the same period as calculated from the table hereunder
January 4 days
February 3 days
March 2 days
April 2 days
May 0 days
June 0 days
July 0 days
August 0 days
September 0 days
October 2 days
November 3 days
December 3 days
The actual number of working days lost due to inclement weather during the construction period shall be determined by the principal agent on a monthly basis (clause 29.1)
Clause 29.11. The removal and replacement of materials and/or workmanship that do not conform to specification or drawings shall not constitute grounds for a revision of the date for practical completion nor for an adjustment to the contract value (clause 29.3)
Clause 29.12 is added: Notwithstanding anything to the contrary the contractor shall not be entitled to a revision of the date for practical completion for delays arising from municipal or other interruption in energy and water supply to the site
Clause 29.12.1 Irrespective of whether or not the principal agent rules that the contractor is entitled to an extension of time or a revision of the date for practical completion, the principal agent shall nevertheless, at any time, be entitled to instruct the contractor in writing to accelerate the progress of the remaining works to ensure that the works are completed by the original date for practical completion or revised date as the case may be
Clause 29.12.2 Upon receipt of such instruction, the contractor shall take all necessary steps to ensure that the works are completed timeously including the provision by him of additional resources, plant, manpower, etc. and the working of additional overtime or additional overtimes beyond that contemplated at the time of tender (at all times adhering to the regulations and requirements of all authorities) and by all other adequate and proper means and methods. The contractor shall prove that such steps are being taken if called upon to do so.
Clause 29.12.3 Should the contractor deem that such instruction to accelerate is not practically possible, the contractor shall within (7) seven calendar days of the instruction provide the principal agent with suitable proof as to why the instructed acceleration is not possible.
10959 | Clause 30.0 - Penalty for late or noncompletion | Item
The penalty for the works that does not reach practical completion by the required date as set out in clause 42.2.8
Clause 30.0 is deemed to be amended by the addition of the following clauses:
30.3 Where the contractor fails to bring the works or sections thereof to works completion within forty (40) working days of the date of the issue the works completion list or revision thereof in terms of clause 30.4, the contractor shall be liable to the employer for the penalty per calendar day for noncompletion of the works at the rate stated in clause 30.7. The principal agent shall calculate the penalty due from and including forty one (41) working days after the date or revised date in terms of clause 30.4 of the issue of the works completion list up to and including the actual date of works completion of the works or section thereof
30.4 The contractor may request additional time for the completion or rectification of works on the works completion list, within 5 working days from receipt of the works completion list, failing which the principal agent shall not consider such claim. The granting of additional time will be by decision of the principal agent
30.5 Where the contractor fails to bring the works or sections thereof to final completion within one hundred and twenty (120) calendar days of the date of the certificate of works completion or revision thereof in terms of clause 30.6, the contractor shall be liable to the employer for the penalty per calendar day for noncompletion of the works or each section thereof at the rate stated in clause 30.7. The principal agent shall calculate the penalty due from and including one hundred and twenty one (121) calendar days after the date of the certificate of works completion or revised date in terms of clause 30.4, up to and including the actual date of final completion of the works or section thereof
30.6 The contractor may request additional time for the completion or rectification of works on the defects completion list, within 5 working days from receipt of the defects completion list, failing which the principal agent shall not consider such claim. The granting of additional time will be by decision of the principal agent
30.7 The penalty will be calculated as follows:
For the works that did not reach works completion or final completion
Penalty amount: R 60 000/calendar day
30.8 Where the employer levies such a penalty the principal agent shall detail the amount for recovery in terms of clause 33.1.1
30.9 The contractor shall agree with the principal agent in writing at least five (5) working days before access to the works is required for the completion or rectification of works on the works completion list. Should the contractor not be allowed access to the works as agreed date the contractor will be granted additional time for completion of the works equal to the time access was refused
PAYMENT (A31 - A35)
11324 | Clause 31.0 - Interim payment to the contractor | Item
Clause 31.0 is deemed to be amended to read as follows:
31.9 The employer shall pay the contractor the amount certified in an interim payment certificate within
thirty (30) calendar days following the date of submission of the contractors payment claim to the quantity surveyor. Payment shall be subject to the contractor giving the quantity surveyor a valid tax invoice for the amount due
Clause 31.9 Delete and replace with following
31.9.1 The employer shall pay the amount certified in an interim payment certificate by the last calendar day of the month, provided that the employer receives the interim payment certificate from the Principal Agent on or before the 5th calendar day of the month for which the services are being rendered, failing which the invoices will be paid by the last calendar day of the following month.
31.9.2 Should the 5th calendar day of the month fall on a weekend or public holiday, documentation should be provided by the first working day subsequent to the 5th calendar day.
31.9.3 Furthermore, the contractor shall ensure that a statement accompanies the invoice issued as per the amount certified by the Pricipal Agent on the all interim payment certificates requested for payment.
31.9.4 No payment will be effected if the contractor is not in possession of a valid Tax Clearance Certificate issued by the South African Revenue Services.
Clause 31.16.1 is deleted
11689 | Clause 32.0 - Adjustment to the contract value | Item
Clause 32.4 is deleted
Clause 32.6 Delete "40" and replace with "20".
Clause 32.0 is deemed to be amended by the addition of the following clauses:
32.16 All fluctuations in costs, with the exception of fluctuations in the rate of Value Added Tax shall be for the account of the contractor. Clause 32.13 shall therefore not apply
32.17 Where prices are submitted by the contractor or nominated/selected subcontractors during the progress of the works in respect of contract instructions or in regard to a claim under the terms of the agreement and notwithstanding the fact that such prices may be used in an interim payment certificate, there is to be no presumption of acceptance. Should the principal agent wish to accept any such prices prior to the issue of the final payment certificate, it will be in writing
12055 | Clause 33.0 - Recovery of expense and loss | Item
Clause 33 is deemed to be amended by the addition of the following clauses:
Clause 33.1.4 is deemed to be deleted
New clause 33.7 shall be added as follows:
33.7 Payment of compensatory interest in terms of 31.10 shall not apply
12420 | Clause 34.0 - Final account and final payment | Item
Clause 34.10 - Delete and replace with following:
34.10.1 The employer shall pay the amount certified in the final payment certificate by the last calendar day of the month, provided that the employer receives the final payment certificate from the Principal Agent on or before the 5th calendar day of the month for which the services are being rendered, failing which the invoices will be paid by the last calendar day of the following month.
34.10.2 Should the 5th calendar day of the month fall on a weekend or public holiday, documentation should be provided by the first working day subsequent to the 5th calendar day.
34.10.3 Furthermore, the contractor shall ensure that a statement accompanies the invoice issued as per the amount certified by the Principal Agent on the final payment certificates requested for payment.
34.10.4 No payment will be effected if client is not in possession of a valid Tax Clearance Certificate issued by the South African Revenue Services.
Clause 34.0 is deemed to be amended by the addition of the following clauses:
34.15 The employer shall not pay any interest on amounts payable to the contractor for one hundred and forty seven (147) working days after the date of issue of the certificate of practical completion. The employer shall, however, pay interest to the contractor at the rate stipulated in clause 34.11 on any amounts payable to the contractor more than one hundred and forty seven (147) working days after the date of issue of the certificate of practical completion but only for such period as the settlement of the final account is delayed by the non-performance of the principal agent or the employer or his agents. In evaluating non-performance for purposes of this clause a reasonable time shall be allowed by the principal agent to the employer or his agents to respond to any matter brought to his/their attention and which may affect the settlement of the final account
12785 | Clause 35.0 - Payment to other parties | Item
CANCELLATION (A36 - A39)
13150 | Clause 36.0 - Cancellation by employer - contractor's default | Item
Clause 36.5.1 is deemed to be amended to read as follows:
36.5.1 The employment of the contractor shall be cancelled and the execution of the works shall cease. The contractor shall vacate the works and the site subject to provisions of 36.5.6. The contractor shall remain responsible for the works as certified at termination, however responsibility for the site shall apply in terms
of Clause 8.1 until possesion is relinquished to the employer
13516 | Clause 37.0 - Cancellation by employer - loss and damage | Item
Clause 37.3.8 - Delete [27.2.2] and replace with [27.2.1]
13881 | Clause 38.0 - Cancellation by contractor - employer's default | Item
Clause 38.1.1 - is deleted
Clause 38.1.4 - is delete
Clause 38.2 Delete "10" and replace with "14".
14246 | Clause 39.0 - Cancellation - cessation of the works | Item
DISPUTE (A40)
14611 | Clause 40.0 - Settlement of disputes | Item
Clause 40.0 is deleted and substituted with the following:
40.1 In the event of any dispute between the parties to this agreement, the parties shall first attempt to resolve the dispute through their respective senior representatives at a meeting, which shall be convened at the written instance of the party declaring the dispute
40.2 If the parties fail to resolve the dispute at a meeting so convened, or such meeting fails to take place, the party declaring the dispute shall be entitled to refer the dispute either for arbitration or to a competent court of law
40.3 Should the party declaring the dispute refer the dispute for arbitration, then the arbitration process shall be conducted in accordance with the arbitration rules and procedures of the Republic of South Africa, and in particular, considering the following:
40.3.1 the parties shall elect or agree to an arbitrator who shall preferably be an attorney with at least fifteen (15) years of
experience in the field of commercial
litigation
40.3.2 the arbitrator shall immediately after appointment, specify the time limits within which the parties must submit any further written submissions or pleadings (if required) and the time, date and place where the arbitration will take place
40.3.3 the arbitrator shall be entitled to make such practical rulings as may be necessary to expedite the proceedings, the intention of the parties being to settle such dispute in the shortest possible time
40.3.4 the finding of the arbitrator shall be final
and binding upon the parties
40.3.5 the arbitrator shall be paid by the parties in such proportions as the arbitrator may decide to be just and equitable under the
circumstances and shall also be entitled to
make a ruling on the share of the costs of
the arbitration to be paid by each party
40.3.6 nothing in this clause shall however prevent a party from approaching a competent court of law for an interdict or similar urgent temporary relief pending the decision of the arbitrator
SUBSTITUTE PROVISIONS (A41)
14977 | Clause 41.0 - State clauses
CONTRACT VARIABLES (A42)
THE SCHEDULE
15342 | Clause 42.0 - Pre-tender information | Item
42.1 CONTRACTING AND OTHER PARTIES
42.1.1 Employer: The Unemployment Insurance Fund represented by the Public Investment Corporation SOC Pty Ltd
Postal address: Private Bag X187
Pretoria
Republic of South Africa
0001
E-mail:enquiries4@pic.gov.za
[1.2] Physical address: Public Investment Corporation
No 1 Central Square
Menlyn Maine
Corner Aramist Avenue & Corobay Avenue
Waterkloof Glen Extension 2
0181
42.1.2 Principal Agent: Project Manager
[5.1]
Physical address:
42.2 CONTRACT DETAILS
42.2.1 Works description: Bulk Earthworks, Lateral Support and Service Relocation for Sunnyside Office Development in Sunnyside Pretoria
42.2.2 Site description:Sunnyside Office Development
The site is situated on Corner Steve Biko And Trevenna Street Sunnyside Pretoria
42.2.3 Work or installations by direct contractors - Yes
[22.2]
42.2.6 Period for the commencement of the works
[15.3] after the contractor takes possession of the
site - 7 working days
42.2.8 For the works in sections: No
[24.3.1] The date for practical completion
[28.1] and the penalty per calendar day
Anticipated Practical Completion March 2020 and the penalty are R 60 000/calendar day
42.2.9 The law applicable to this agreement shall be
[1.2] that of the Republic of South Africa. The Jurisdiction of the Gauteng Provincial Division of the High Court
of South Africa shall be applicable in respect of any disputes arising out of this agreement
42.3 INSURANCES
42.3.1 Contract works insurance (including SASRIA) to be
effected by the Contractor
For the sum of: Contract sum plus 20%
With deductible for any one occurrence in accordance with
the insurance companys excess.
42.3.2 Supplementary insurance in respect of neighbouring
buildings due to blasting to be effected by Contractor
For the sum of the contract sum plus 20%
With deductible for any one occurrence in accordance with
the insurance companys excess.
42.3.3 Public liability insurance to be effected by the
Contractor
For the sum of: R 15 000 000.00
With deductible for any one occurrence in accordance with
the insurance companys excess.
42.3.4 Lateral Support insurance to be effected by - Yes
Contractor
For the sum of the replacement value of the adjoining
properties.
With deductible for any one occurrence in accordance with
the insurance companys excess.
42.4 DOCUMENTS
42.4.1 Waiver of the contractor's lien or right of
[3.3, continuing possession is required - Yes
15.1.3,
31.16.2#]
42.4.2 Construction document copies to
[3.7] be supplied to the contractor free of charge
No of 0. (Documents including drawings will be issued electronicaly).
42.4.3 Provisional Bills of quantities are drawn up in
[1.1] accordance with the latest edition of the City of Tshwane Standard Specifications For Municipal Civil Engineering Works 3rd Edition 2005
42.4.4 N/A
42.4.5 JBCC Engineering General Conditions are
[3.4] to be included in the contract documents - No
42.4.6 The contract value is to be adjusted using
[31.5.3] CPAP indices - No
[32.13] Fixed price rates not subject to adjustment by CPAP
42.4.7 Details of changes made to the provisions
[3.10] JBCC Standard documentation
Refer to Preliminaries and General section of the Bill of Quantities for all changes made to the JBCC Agreement.
Clause 42.0 - Post - tender information
42.5 Contract details
42.5.1 Contractor:
[1.2] Physical address:
42.5.2 The accepted contract sum inclusive of tax is:
R
42.5.3 The latest day of the month for the issue of an
[31.3] interim payment certificate (day of month): 5th of the month
42.5.4 The preliminaries amounts shall be paid in
[32.12] terms of (option A or B): B
42.5.5 The preliminaries amounts shall be adjusted
[32.12] in terms of (option A or B): A
42.5.6 The payment guarantee to be effected by the
[3.1#] employer for the sum of: N/A
42.5.7 The securities to be provided by the contractor are:
[14.3] (1) Variable construction guarantee (yes/no): Yes
[14.4] (2) Fixed construction guarantee (yes/no): No
[14.5] (3) Advance payment guarantee (yes/no): No
42.5.8 The annual building holiday period after
[29.7.2] the commencement of the construction period is as follows:
13 December 2019 - 13 January 2020
42.6 Documents
42.6.1 Contract documents marked and annexed hereto:
(Refer to Index for all annexed)
42.6.2 Signed set of contract documents originals
[3.6.1#] held by principal agent - yes
42.7 Dispute resolution
42.7.1 Refer to clause 40.0 herein
42.7.2 Where adjudication is elected: Refer clause 40.0 herein
42.7.3 Where arbitration is elected or is required in terms of 40.5: Refer to clause 40.0 herein
42.7.4 Where mediation is elected in terms of 40.6: N/A
42.8 Signatures of the contracting parties: Refer to Principal Building Agreement
SECTION B - PRELIMINARIES
DEFINITIONS AND INTERPRETATION (B1)
15707 | Clause 1.0 - Definitions and interpretation | Item
DOCUMENTS (B2)
16072 | Clause 2.1 - Checking of documents | Item
16438 | Clause 2.2* - Provisional bills of quantities | Item
Clause 2.2 is deemed to be amended by the addition of the following paragraph:
These bills of quantities are in the Multiple Procurement format i.e. the bulk earthworks, lateral support and service relocation are provisionally measured and the subsequent trades are budgetary allowances and subcontract amounts
16803 | Clause 2.3* - Availability of construction documentation | Item
Clause 2.3 is deemed to be amended by the addition of the following paragraph:
The budgetary allowances and subcontract amounts allocated for subsequent trades included in this document will be separately procured, based on multiple procurement of nominated/selected subcontractors during the construction period
17168 | Clause 2.4* - Interests of agents | Item
17533 | Clause 2.5 - Priced documents | Item
17899 | Clause 2.6 - Tender submission | Item
Clause 2.6 is deemed to be amended by the addition of the following paragraph:
Notwithstanding anything contained in this clause, tenders shall be valid for a period of 90 calendar days from the tender closing date
THE SITE (B3)
18264 | Clause 3.1* - Defined works area | Item
18629 | Clause 3.2* - Geotechnical investigation | Item
18994 | Clause 3.3 - Inspection of the site | Item
The contractor shall take full responsibility and accordingly indemnify the employer in respect of any failure by the contractor to adequately inspect the site and no claims by the contractor shall be entertained resulting from such failure
19360 | Clause 3.4* - Existing premises occupied | Item
19725 | Clause 3.5* - Previous work - dimensional accuracy | Item
20090 | Clause 3.6* - Previous work - defects | Item
20455 | Clause 3.7* - Services - known | Item
20821 | Clause 3.8 - Services - unknown | Item
21186 | Clause 3.9* - Protection of trees | Item
21551 | Clause 3.10 - Articles of value | Item
21916 | Clause 3.11* - Inspection of adjoining properties | Item
MANAGEMENT OF CONTRACT (B4)
22282 | Clause 4.1 - Management of the works | Item
22647 | Clause 4.2 - Programme for the works | Item
23012 | Clause 4.3 - Progress meetings | Item
23377 | Clause 4.4 - Technical meetings | Item
23743 | Clause 4.5 - Labour and plant records | Item
SAMPLES, SHOP DRAWINGS AND MANUFACTURER'S INSTRUCTIONS (B5)
24108 | Clause 5.1 - Samples of materials | Item
24473 | Clause 5.2 - Workmanship samples | Item
24838 | Clause 5.3 - Shop drawings | Item
25204 | Clause 5.4 - Compliance with manufacturer's instructions | Item
TEMPORARY WORKS AND PLANT (B6)
25569 | Clause 6.1 - Deposits and fees | Item
25934 | Clause 6.2* - Enclosure of the works | Item
26299 | Clause 6.3 - Advertising | Item
26665 | Clause 6.4 - Plant, equipment, sheds and offices | Item
27030 | Clause 6.5* - Main noticeboard | Item
27395 | Clause 6.6* - Subcontractors' noticeboard | Item
TEMPORARY SERVICES (B7)
27760 | Clause 7.1 - Location | Item
28126 | Clause 7.2# - Water | Item
28491 | Clause 7.3# - Electricity | Item
28856 | Clause 7.4# - Telecommunication facilities | Item
29221 | Clause 7.5# - Ablution facilities | Item
PRIME COST AMOUNTS (B8)
29587 | Clause 8.1 - Responsibility for prime cost amounts | Item
ATTENDANCE ON N/S SUBCONTRACTORS (B9)
29952 | Clause 9.1 - General attendance | Item
30317 | Clause 9.2* - Special attendance | Item
30682 | Clause 9.3 - Commissioning - fuel, water and electricity | Item
FINANCIAL ASPECTS (B10)
31048 | Clause 10.1 - Statutory taxes, duties and levies | Item
31413 | Clause 10.2# - Payment of preliminaries | Item
31778 | Clause 10.3# - Adjustment of preliminaries | Item
Clause 10.3 is deemed to be amended by the addition of the following paragraph:
Should the contractor select option B but fails to provide the information required prior to the signing of the agreement, the principal agent shall have the right to select either option A or B for the adjustment of preliminaries. Should the principal agent select option B he shall be entitled to make assumptions at his discretion regarding the information which the contractor would normally have provided prior to the signing of the agreement
32143 | Clause 10.4 - Payment certificate cash flow | Item
GENERAL (B11)
32509 | Clause 11.1* - Protection of the works | Item
32874 | Clause 11.2* - Protection/isolation of existing/sectionally occupied works | Item
33239 | Clause 11.3 - Security of the works | Item
33604 | Clause 11.4 - Notice before covering work | Item
33970 | Clause 11.5* - Disturbance | Item
34335 | Clause 11.6 - Environmental disturbance | Item
34700 | Clause 11.7 - Works cleaning and clearing | Item
35065 | Clause 11.8 - Vermin | Item
35431 | Clause 11.9 - Overhand work | Item
35796 | Clause 11.10 - Instruction manuals and guarantees | Item
36161 | Clause 11.11 - As built information | Item
1/1/100 | Clause 11.12 - Tenant installations | Item
SCHEDULE OF VARIABLES (B12)
1/1/101 | Clause 12.1 - Pre-tender information | Item
Where no information is given it shall mean that either no details or specific requirements are available or if so indicated that the clause is not relevant to this specific contract
Clause 12.1.1 - Provisional bills of quantities [B2.2]
The quantities are provisional - yes
Clause 12.1.2 - Availability of construction documentation [B2.3]
Construction documentation is complete - No
Clause 12.1.3 - Interests of agents [B2.4]
Clause 12.1.4 - Defined works area [B3.1]
Clause 12.1.5 - Geotechnical investigation [B3.2]
The geotechnical report was prepared by GCS Geotechnical
and was annexed to the tender enquiry document
Clause 12.1.6 - Existing premises are not occupied during construction [B3.4]
Clause 12.1.7 - Previous work - dimensional accuracy [B3.5]
Clause 12.1.8 - Previous work - defects [B3.6]
Clause 12.1.9 - Services - known [B3.7]
Clause 12.1.10 - Protection of trees [B3.9]
Clause 12.1.11 - Inspection of adjoining properties [B3.11]
In addition to the requirements of Clause B3.11 a photographic survey the conditions of the adjoining buildings, roads, etc. Shall be compiled cooperation with the Employer's agents.
Clause 12.1.12 - Enclosure of the works [B6.2]
Specific Request:
Site perimeter hoarding has to be included in this Contract and must be erected. This hoarding will be taken over and maintained by the main contractor at the end of the bulk earthworks and lateral support contract.
Temporary Hoarding 2000mm high above ground level over flat
or sloping terrain including 0.5mm galvanised corrugated
sheeting fixed to SABS CCA treated poles 100/125mm
2400mm high at 2000mm centres cast into concrete bases
executed complete (296m). Including 6000mm x 1800mm high gate including steel frame, corrugated sheet, bolts and pad locks, etc.
Clause 12.1.13 - Offices [B6.4.3]
Clause 12.1.14 - Main noticeboard [B6.5]
Clause 12.1.15 - Subcontractors' noticeboard [B6.6]
A notice board is required - Yes
Clause 12.1.16 - Water [B7.2]
Option selected: A Contractor
Clause 12.1.17 - Electricity [B7.3]
Option selected: A Contractor
Clause 12.1.18 - Telecommunications [B7.4]
Telephone (yes)
Facsimile (yes)
E-mail (yes)
Clause 12.1.19 - Ablution facilities [B7.5]
Option selected: A Contractor
Clause 12.1.20 - Protection of existing/sectionally
occupied works [B11.2]
Protection is required - no
Clause 12.1.21 - Special attendance [B9.2]
Clause 12.1.22 - Protection of the works [B11.1]
Clause 12.1.23 - Disturbance [B11.5]
Clause 12.1.24 - Environmental disturbance [B11.6]
1/1/102 | Post-tender information [B12.2] | Item
Clause 12.2.1 - Payment of preliminaries [B10.2]
Option selected:
Clause 12.2.2 - Adjustment of preliminaries [B10.3]
Option selected:
Clause 12.2.3 - Additional agreed preliminaries items
SECTION C - SPECIFIC PRELIMINARIES
1/1/103 | Clause C1 - Confidentiality | Item
The contractor undertakes to maintain in confidence any and all information regarding this project and shall obtain appropriate similar undertakings from all subcontractors and suppliers. Such information shall not be used in any way except in connection with the execution of the works
No information regarding this project shall be published or disclosed without the prior written consent of the employer
1/1/104 | Clause C2 - Contract instructions | Item
Contract instructions issued are to be recorded in triplicate in a contract instruction book which is to be supplied and maintained on site by the contractor. The top copy must remain on the site until it is countersigned by the principal agent and will only become a legal contract instruction once signed by the principal agent
1/1/105 | Clause C3 - Guarantees | Item
Where guarantees are called for, the contractor shall obtain a written guarantee, addressed to the employer, from the firm supplying the materials and/or doing the work and shall deliver same to the principal agent not later than the works completion date. The guarantee shall state that workmanship, materials and installation are guaranteed for a specified period from the final completion date and that any defects that may arise during the specified period shall be made good at the expense of the firm supplying the materials and/or doing the work, upon written notice from the principal agent to do so. This guarantee will not be enforced if the work is damaged by defects in the construction of the building in which case the responsibility for replacement shall rest entirely with the contractor. The principal agent shall be the sole judge of the cause responsible for defects in the works and his decision shall be final and binding in terms of clause A40.2 of the agreement
1/1/106 | Clause C4 - User requirements | Item
There is a possibility that certain works related to users' requirements may have to be delayed and may consequently not be executed prior to the dates of practical completion
The employer reserves the right to omit such work without compensation to the contractor for any loss which may be incurred as a result of such omission. Should the contractor be instructed to do so he shall execute this work under the conditions pertaining to this agreement on the basis that a separate amount for preliminaries appurtenant to this work (if applicable) is agreed to between the contractor and the principal agent and on condition that instructions to proceed with such work is given to him within a period of three (3) calendar months after date of practical completion of the works
1/1/107 | Clause C5 - Overtime | Item
Should overtime be required to be worked for any reason whatsoever, the costs of such overtime is to be borne by the contractor unless the principal agent has specifically authorised, in writing, prior to execution thereof, that costs for such overtime are to be borne by the employer
1/1/108 | Clause C6 - Co-operation of contractor for cost management | Item
It is specifically agreed that the contractor accepts the obligation of assisting the agents in implementing proper cost management on this project. The contractor will be advised by the principal agent of all cost management procedures which will be implemented to ensure that the final account does not exceed the budget
1/1/109 | Clause C7 - Control of sand, dust, mud, light and noise pollution on site, public spaces, public roads, etc | Item
The contractor shall be responsible for and take all precautions in controlling all forms of pollution during the contract period due to noise, artificial light, wind-blown sand, dust, etc in the dry season and deposits of mud etc in the wet season by whatever means necessary and daily removal of deposits etc, all to the satisfaction of the principal agent and any costs, claims, etc will be for the contractor's account
1/1/110 | Clause C8 - Environmental Management Plan | Item
The contractor shall be responsible for and take all precautions in controlling all requirments in terms of the Environmental Management Plan during the contract period, all to the satisfaction of the principal agent and any costs, claims, etc will be for the contractor's account
1/1/111 | Clause C10 - Local Labour | Item
The contractor shall make use of local labour. It is desirable by the employer that all unskilled labour be recruited from the local areas of the vicinity of the works. The contractor will demonstrate his effort to fulfill compliance with this requirement
1/1/112 | Clause C11 - Joint Venture Requirement | Item
The employer is open to consider bidders that form or already have an existing Joint Venture/Consortium agreement in place to achieve a Broad Based Black Economic Empowerment Status Level. For Joint Venture/Consortium the following additional information will be required:
· Consolidated Generic BEE Certificate.
· Ownership and Executive Management information.
· A formal signed JV Agreement, indicating the leading company as well as the other companys role and responsibilities.
· Skills transfer plan between the parties must be submitted.
1/1/113 | Clause C12 - GREEN STAR | Item
The contractor to make necessary allowances for works relating to Green Star building requirements.
Clause C13: GENERAL
Clause 13.1: Contractor to be responsible
The contractor acknowledges that the principal objective of his appointment is his expert knowledge in the execution of the scope of work of this contract. The contractor shall be solely responsible for all aspects of the construction of the works including but not limited to management, resourcing, programming and co-ordination of sequencing of work all as required for the type of project described and within the time limits and quality standards specified.
Clause 13.2: Notice Boards, Media Releases, Advertising, Etc.
All rights of publication of articles in the media, together with any advertising relating to, or in any way connected with this project, shall vest with the employer.
The contractor together with his subcontractors shall not, without the written consent of the employer, cause any statement or advertisement to be printed, screened or aired by the media, or have any advertising signage displayed on site.
Clause 13.3: Method Statement
The contractor shall produce, when required to do so by the principal agent, a method statement outlining the methods of construction and labour and plant resources that he proposes to use in the execution of the works. Any approval given or observation made by the principal agent shall not relieve the contractor of his sole responsibility to adopt the methods of construction and to provide the labour and plant resources necessary for the due and proper timeous execution of the works.
Clause 13.4: Overloading
The contractor shall take all necessary steps to ensure that no damage occurs due to overloading of any portion of the works or temporary works, scaffolding, etc. The contractor shall submit details of his proposed loading, storage, plant erection, etc., to the principal agent for their approval prior to proceeding with such loading, storing or erecting and shall comply with and pay for the principal agents requirements in connection with the provision of temporary support work, etc. Any damage caused to the works by overloading shall be made good by the contractor at his sole expense.
Clause 13.5: Structural Safety
The contractor shall take all reasonable measures to ensure that all alteration works are structurally practicable and safe. The contractor shall provide and price under the relevant demolition item, for all necessary temporary propping and support which may be required.
Clause 13.6: Condemned Work
The contractor shall remove from the site all materials not conforming to the relevant specification and condemned by the principal agent, whether incorporated in the works or not. He shall replace such material and re-execute the affected work in accordance with the contract and without expense to the employer. The contractor shall also bear the expense of making good any other work damaged or destroyed by such removal or replacement
Clause 13.7: Photographic Record
A two weekly photographic record is to be provided by the contractor, recording the state of progress of the works. Copies of each photograph annotated with the location and date, are to be made available to the employer via the principal agent.
Clause 13.8: Mode of Procedure
Notwithstanding anything to the contrary contained herein, the principal agent at all times reserves the right to direct the order in which the various parts of the contract are to be executed. The contractor shall give priority to any individual section or portion of the works that, in the opinion of the principal agent, requires to be expedited.
Should the contractor and/or principal agent be of the opinion that such instruction warrants a revision of date for practical completion and / or an adjustment to the contract value then this will be dealt with in terms of clause 29 and clause 32.
Should it appear, in the principal agents opinion, that work in any area is not being executed in accordance with the requirements of the programme, the contractor shall provide additional manpower and resources and shall work additional overtime and do everything else required to bring the work back to programme to the satisfaction of the principal agent.
Clause 13.9: Continuous Supply of Electricity
The contractor shall allow for the provision of suitable standby generated power including all connection, fuel and maintenance costs to meet the requirement of the contract.
Clause 13.10: Royalties, Patent Rights and Fees
The contractor shall indemnify the principal agent against any action, claim, demand, costs or expenses arising from or incurred by reason of any infringement of letters, patent design, trademark, name, copyright or other protected rights in respect of any machine, plant, work, materials, thing, system or method of using, fixing, working or arrangement used or fixed or supplied by the contractor, but such indemnity shall not cover any use of the equipment or part thereof otherwise than in accordance with theprovisions of the specification.
All payments and royalties payable in one sum or by instalments or otherwise, shall be included by the contractor in the price and shall be paid by him to those to whom they may be due or payable.
In the event of any claim being made or action brought against the principal agent arising out of the matter referred to in this clause, the contractor shall be promptly notified thereof and may, at his own expense, conduct negotiations for the settlement of the same and/or litigation, that may arise therefrom. The principal agent shall not, unless and until the contractor shall have failed to take over and conduct the negotiations of litigation, make any admission which might be prejudicial thereto.
The conduct by the contractor of such negotiations or litigation shall be conditional upon the contractor having first given the principal agent such reasonable security as shall from time to time be required by the principal agent, to cover the amount ascertained or agreed or estimated, as the case may be, or any compensation, damage, expenses and costs for which the principal agent may become liable in respect of such infringement as aforesaid. The principal agent shall, at the request of the contractor, afford all available assistance for the purpose of contesting any such claim or action and shall be repaid the expenses incurred in doing so.
The conduct by the contractor of such negotiations or litigation shall be conditional upon the contractor having first given the principal agent such reasonable security as shall from time to time be required by the principal agent, to cover the amount
ascertained or agreed or estimated, as the case may be, or any compensation, damage, expenses and costs for which the principal agent may become liable in respect of such infringement as aforesaid. The principal agent shall, at the request of the contractor, afford all available assistance for the purpose of contesting any such claim or action and shall be repaid the expenses incurred in doing so.
Clause C14: INTERFERENCE WITH TRAFFIC FLOW AND NEARBY PROPERTIES
All operations necessary for the execution of the works and for the construction of any temporary works shall not interfere unnecessarily or improperly with the access of the public to permanent roads and footpaths.
The Contractor shall indemnify the Employer in respect of all claims, demands, proceedings, damages, costs, charges and expenses whatsoever arising out of or in respect of or in relation to any such matters.
The Contractor shall at all times accommodate such provisions as may be necessary in the opinion of the Principal Agent to ensure that disruption to the occupants of the nearby buildings or the public is kept to an absolute minimum.
The Contractor shall make all necessary provisions in his rates for his requirements and no additional entitlement on the part of the Contractor in compliance with these requirements shall be entertained.
The Contractor must reinstate the existing streets, pavings, kerbs, etc. to their original condition on completion of the building operations to the satisfaction of the Principal Agent.
The programme must be structured in such a way to keep the disruption to traffic as little as possible.
Sufficient signs shall be erected to re-direct traffic where the road is closed off for construction including flag workmen, traffic signs as per the drawings.
Clause C15: BLASTING OPERATION
The contractor is deemed to have accepted full responsibility during any blasting operations that may be carried out, should blasting be permitted. The Contractor shall take all necessary precautions for the safety of all persons, buildings, etc. and is to observe all conditions set forth in Government and Local Authorities regulations
in connection with the use of explosives and pay all costs and fees. All blasting is to be carried out by a licensed blaster.
Clause C16: INFRINGEMENT WARRANTY
The Contractor hereby:
Warrants to the Employer that he has the right to perform the contract works;
Warrants that in so performing the contract works that he shall not infringe the rights of any other person.
Clause C17: SITE OFFICE FOR USE BY CLIENT AND CLIENTS CONSULTANTS
The Contractor to provide Air conditioned office accommodation for meetings suitable for 20 persons as well as additional air conditioned office space for two workstations complete with desks , internet data connection and chairs. The office accommodation is to be kept clean and fit for use at all times.
CLAUSE C18 ADDITIONAL PRELIMINARY REQUIREMENTS
Note:
The condition of Contract and Payment Condition shall be in accordance with the Principal Building Agreement as detailed in the above Preliminary and General Items. The method of measurements and payment of items in the Bills of Quantities shall be in accordance with the specifications and the document titled "Standard Specifications for Municipal Civil Engineering Works".The tenderer must price against the following items for any cost associated with complying with the requirements of the above documents, where such requirements are not covered by the Preliminary and General in section A, B and C above
1/1/114 | GENERAL (Series 0) | Item
Section 001: General Requirements and Preliminary & General charges compliance
-1.01
1/1/115 | Locate existing services | Item
1.02
1/1/116 | Extra over item 001.02, location of existing services for cross cuts as per City of Tshwane requirements and specifications for wayleave approval. | Item
PIC001.02.01
1/1/117 | Excavate by hand to expose existing services and backfill | Item
1.03
1/1/118 | Extra over item 001.03, excavate by hand to expose existing services and backfill cross-cuts as per CoT requirements for wayleave approval | Item
Environmental Management
PIC001.06
1/1/119 | Compliance with Environmental Management Plan | Item
PIC001.06.01
1/1/120 | Environmental Control Officer | Item
PIC001.06.02
Additional survey requirements
1/1/121 | Survey by contractor to determine setting out coordinates to engineers approval | Item
PIC 002.04.01
1/1/122 | Checking and confirmation of survey of setting out details by independent contractor to engineers approval | Item
PIC 002.04.02
Documents Managements
1/1/123 | All documentation for this project to be managed and controlled | Item
with BIM 360 and the contractor is to make his own
arrangements and allow all cost associated in complying with
the requirements.
Community liaison officer
1/1/124 | Monthly Wage COT Level rate p/m | Item

## P&G Summary
| BILL NO 1 - PRELIMINARY AND GENERAL | Page No |  | Amount
01 | PRELIMINARIES | -50-
| TOTAL CARRIED TO FINAL SUMMARY |  | R

## Section 101
Item No | Description | Unit | Quantity | Rate | Amount
BILL NO 2 - BULK EARTHWORKS
SERIES 1 | ANCILLARY WORK
Section 101 | Site Clearing and Grubbing
101.01.01 | Areas | m² | 10361
101.01.02 | Strips up to 1m wide | m | 1072
101.02 | Cutting and removing large trees
with a girth -
101.02.01 | exceeding 1m and up to and | no | 11
including 2m
101.02.02 | exceeding 2m and up to and | no | 0
including 3m
101.03 | Grubbing and the removal of the
girth -
101.03.01 | exceeding 1m and up to and | no | 11
including 2m
101.03.02 | exceeding 2m and up to and | no | 0
including 3m
101.04 | Re-clearing of areas (only on the
101.04.02 | Areas not classified as strips | m² | 0
101.05 | Removal and disposal of specific
elements
101.05.01 | Concrete kerbing / kerbing
| combinations | m | 525
101.05.02 | Concrete or brick elements
(reinforced or unreinforced)
101.05.02.01 | 230mm brickwork | m² | 0
101.05.02.02 | 115mm brickwork | m² | 0
101.05.02.01 | Concrete elements (unreinforced) | m³ | 2385
101.05.02.02 | Concrete elements (reinforced) | m³ | 804
101.05.02.03 | Brick structures (incl walls) | m³ | 50
101.05.03 | Asphalt surfacing | m² | 981.5
PIC101.05.04 | Interlocking / non-interlocking
| paving blocks | m² | 1120
PIC101.07 | Removal and disposal of rubble
| not measurable elsewhere | m³ | 500
| Total Carried to Summary |  |  | R

## Section 202
Item No | Description | Unit | Quantity | Rate | Amount
SERIES 2 | EARTHWORKS
Section 202 | Trenching
202.01, PIC 202.01 | Trench excavation
202.01.01 | 0m to 1,0m wide
202.01.01.01 | Up to 1,0m deep | m³
202.01.01.02 | Over 1,0m deep and up to 1,5m deep | m³ | 851
202.01.01.03 | Over 1,5m deep and up to 2,0m deep | m³ | 409
202.01.01.04 | Over 2,0m deep and up to 2,5m deep | m³ | 1180
202.01.01.05 | Over 2,5m deep and up to 3,0m deep | m³ | 536
202.01.01.06 | Over 3,0m deep and up to 3,5m deep | m³ | 0
202.01.01.07 | Over 3,5m deep and up to 4,0m deep | m³ | 0
202.01.01.08 | Over 4,0m deep and up to 4,5m deep | m³ | 0
202.02 | Extra over items 202.01 for excavating in:
202.02.01 | Intermediate excavation | m³ | 273
202.02.02 | Hard material | m³ | 1783
202.03 | Excavations and backfill outside the normal trench profile | m³ | 72
202.04 | Hand Excavation (Extra over 202.01) | m³ | 540
202.06 | The backfilling of trenches excluding backfill around pipe barrel with material obtained from excavation. | m³ | 1425
202.07 | Extra over items 202.06
for using backfill material obtained
202.07.01 | From borrow areas | m³ | 557
202.07.02 | From sources provided | m³ | 526
(reinforced or unreinforced)
202.1 | Removal of spoil material -
202.10.01 | To positions indicated on | m³ | 295
the Drawings or by the Engineer.
202.10.02 | To dumping areas to be | m³ | 304
provided by the Contractor
202.12 | Extra over item 202.06 for additional
compaction of backfill to 93% of
modified AASHTO density in road
| reserves | m³ | 100
202.15 | Reinstatement of bitumen surfaced
| roads | m² | 981.5
202.16 | Extra over item 202.01 for backfilling using stabilized material | m³
| Total Carried to Summary |  |  | R

## Section 203
ITEM | DESCRIPTION | UNIT | QTY | RATE | AMOUNT
SERIES 2 | EARTHWORKS
Section 203 | Mass Earthworks
Ref Dwgs: 1600073-08-81-C-501 - 522
203.01 | Excavation and borrow to fill | -50-
including to stockpile
B203.01.01 | Compaction to 93% of modified
| AASHTO density | m³ | 0
203.02 | Extra over item 203.01 for excavating
in -
203.02.01 | Intermediate material | m³
203.02.02 | Hard material | m³
203.02.03 | Boulder material class A | m³ | 0
203.02.04 | Boulder material class B | m³ | 0
203.03, PIC 203.03, PIC 203.03A | Excavate and spoil of -
203.03.01 | Soft material | m³ | 60879.5
203.03.02 | Intermediate material | m³ | 73359
203.03.03 | Hard material | m³ | 58391.3
203.03.04 | Boulder material class A | m³ | 20135.775
203.03.05 | Boulder material class B | m³ | 20135.775
| Total Carried to Forward |  |  | R
ITEM | DESCRIPTION | UNIT | QTY | RATE | AMOUNT
| Total Brought Forward |  |  | R
203.08 | Preparation and compaction of
construction bed material to 90% of
| modified AASHTO density | m³ | 500
203.10, PIC 203.10 | In situ treatment of the construction
bed
203.10.01 | In situ treatment by ripping | m³
203.10.01 | In situ treatment by ripping | m³ | 1541.25
203.10.02 | In situ treatment by blasting | m³ | 3082.5
203.11, PIC 203.11 | Finishing off slopes
203.11.01 | Excavation slopes | m² | 8211
203.11.02 | Fill slopes | m² | 400
| Total Carried to Summary |  |  | R

## Section 302
Item No | Description | Unit | Quantity | Rate | Amount
SERIES 3 | SEWERS
Section 302 | Construction
Ref Dwgs: 1600073-08-81-C-201
302.01, PIC 302.01 | Supplying, laying and jointing of sewer
pipes irrespective of depth or width
of trench
301.01.01 | 250mm uPVC PIPE 400kPa (SABS 1601) | m | 220
301.01.02 | 315mm uPVC PIPE 400kPa (SABS 1601) | m | 70
301.01.01 | 110mm Duroflo PVC-U Pressure Pipe | m | rate only |  | ro
Systems (SANS 966-1)
301.01.02 | 160mm Duroflo PVC-U Pressure Pipe | m
Systems (SANS 966-1)
301.01.03 | 250mm Ductile iron Pipe (rising main) | m | rate only |  | ro
Systems (SANS 966-1)
302.02 | Constructing of pipe beddings
302.02.01 | Class B bedding
302.02.01.01 | 250mm uPVC PIPE Class 34 | m3 | 84.15
301.02.01.02 | 315mm uPVC PIPE Class 34 | m3 | 29.75
302.03 | Concrete encasing of pipes | m3 | 25
302.06 | Construction of vertical
Ref Dwgs: 7515-S206
302.06.02 | Type D (4) house connections:
302.06.02.02 | Exceeding 1,5m but not exceeding
| 2,0 m in depth | No | 4
302.08 | Marker blocks | No | 2
302.09 | (reinforced or unreinforced)
deep
302.09.01 | For sewers 315mm in diameter and
smaller
302.09.01.01 | 1.2m diameter manhole, refer to | No | 3
Dwg CoT -7515-S101
302.10 | Extra-over item 302.09 for the
construction of manholes in excess
of 1.0m deep
Ref Dwgs: 7515-S203
302.10.01 | For sewers 315mm in diameter and | No | 7
smaller
302.12 | Supplying and installing manhole
covers and frames
302.12.01 | SANS 558 Type 4 circular (CI) | No | 3
302.12.02 | SANS 558 Type 2A circular (CI) | No | rate only |  | ro
302.12.03 | Precast concrete cover with type 2A | No | 10
CI frame
302.12.04 | Precast concrete cover with type 4 | No | 10
CI frame
| Total Carried to Forward |  |  | R
Item No | Description | Unit | Quantity | Rate | Amount
| Total Brought Forward |  |  | R
302.14 | Supplying and placing selected
backfill material around and up to
to 300mm above pipe barrels
using
302.14.01 | Excavated material | m3 | 25
302.14.02 | Imported material | m3 | 10
302.16 | Connecting to existing manholes
Ref Dwgs: 7515-S210
302.16.01 | 250mm pipe diameter, all classes | No | 15
302.16.02 | 315mm pipe diameter, all classes | No | 15
302.20 | Preliminary work prior to the
construction of a manhole on an
existing pipeline
302.20.01 | 250mm UPVC sewer pipe | No | 15
302.20.02 | 315mm UPVC sewer pipe | No | 15
302.20.03 | 900mm Duroflo Concrete Pipe | No | rate only |  | ro
using material obtained from
| Total Carried to Summary |  |  | R

## Section 303
Item No | Description | Unit | Quantity | Rate | Amount
SERIES 3 | SEWERS
Section 303 | Testing
303.01 | Testing of manhole | No | 7
303.02 | Air testing of sewers
303.02.02 | 250mm | m | 220
303.02.02 | 315mm | m | 70
| Total Carried to Summary |  |  | R

## Section 402
Item No | Description | Unit | Quantity | Rate | Amount
SERIES 4 | WATER RETICULATION AND WATER MAINS
Ref Dwgs: 1600073-08-81-C-101
Section 402 | Construction
402.01, PIC 402.01 | Supplying, laying and jointing of water pipes
irrespective of depth:
402.01.01 | PVC-U class 12 pipes with spigot and socket
joints
402.01.01.01 | 22.5mm Ø | m
402.01.01.02 | 50mm Ø | m
402.01.01.03 | 75mm Ø | m
402.01.01.04 | 160mm Ø | m
402.01.01.05 |  | m
402.01.01.06 | 250mm Ø | m | 667
402.01.01.07 | 300mm Ø | m
402.01.02 | Threaded galvanised steel pipe
402.01.02.01 |  | m | rate only |  | ro
402.01.03 | Polyethylene pipes
402.01.03.01 | 50 mm Ø Class 12 | m | rate only |  | ro
402.02.01 | Bends (Class 12)
402.02.01.01 | 250mm Ø x 11,25 deg | No | 20
(reinforced or unreinforced)
402.02.01.02 | 250mm Ø x 22.5 deg | No | 20
402.02.01.03 | 250mm Ø x 45 deg | No | 20
402.02.01.04 | 250mm Ø x 90 deg | No | 20
402.02.02.02 | 250mm Ø - 160mm Ø unequal tees | No | 7
402.02.04 | End caps (Class 12)
402.02.04.02 | 250mm Ø | No | 20
| Total Carried to Forward |  |  | R
402.02.07 | Single air valves complete
402.02.06.01 | 50mm Ø | No | rate only |  | ro
ITEM | DESCRIPTION | UNIT | QTY | RATE | AMOUNT
LI 402.03 | Encasement of pipes with :
402.03.01 | Class 15/19 concrete | m³ | 12.5
402.03.02 | Soilcrete | m³ | 10
| Total Brought Forward |  |  | R
402.04 | Providing thrust blocks using class 15/19 concrete | m³ | 1
Ref Dwgs: 7515-W210
402.05 | Supplying and placing unscreened selected backfill material under, alongside and up to 300 mm above pipe barrels using:
Ref Dwgs: 7515-W211
402.05.01 | Material from trench excavations, other trenches or other excavations required for the project | m³ | 26
402.05.02 | Material from commercial sources | m³ | 26
402.06 | Extra over item 402.05 for
screening excavated
material for selected
| backfill | m³ | 10
402.07 | Valve chambers complete for -
Ref Dwgs: 7515-W203
402.07.01 | Gate valves not exceeding 250 mm in dia:
402.07.02.01 | 250 mm Ø | No | 5
402.08 | Installation of marker blocks
Ref Dwgs: 7515-W203
402.08.01 | Concrete marker blocks | No | 2
402.09 | Installation of hydrants complete as per | No | 2
as per standard Dwg 7515- 2-W
402.10 | Sterilizing of pipelines
402.10.01 | 250mm Ø | m | 667
402.10.02 | 50mm Ø | m | 350
402.10.03 | 75mm Ø | m | rate only |  | ro
| Total Carried to Forward |  |  | R
ITEM | DESCRIPTION | UNIT | QTY | RATE | AMOUNT
402.10.04 | 160mm Ø | m | rate only |  | ro
402.10.05 | 250mm Ø | m | rate only |  | ro
402.10.06 | 300mm Ø | m | rate only |  | ro
402.10.07 | 450mm Ø | m | rate only |  | ro
402.10.08 | 700mm Ø | m | rate only |  | ro
| Total Brought Forward |  |  | R
B402.12 | Miscellaneous items
B402.12.01 | Connect to existing reticulation and switch over to new system. | Lump sum | 1
B402.12.02 | Remove and replace existing water
connections and meters for pipe diameters:
402.12.02.01 | 50mm | No | 10
402.12.02.02 | 110mm | No | 10
402.12.02.03 | 160mm | No | 10
402.12.02.04 | 200mm | No | 10
402.12.02.05 | 250mm | No | 10
| Total Carried to Summary |  |  | R

## Section 403
Item No | Description | Unit | Quantity | Rate | Amount
SERIES 4 | WATER RETICULATION AND WATER MAINS
SECTION 403 | SECTION 403 : TESTING
403.01 | Hydraulic field-testing of pipelines
403.01.01 | up to 75mm Ø | m | 350
403.01.02 | 110mm Ø | m | 100
403.01.03 | 160mm Ø | m | rate only |  | ro
403.01.04 | 200mm Ø | m | rate only |  | ro
403.01.01 | 250mm Ø | m | 667
403.01.03 | 300mm Ø | m | rate only |  | ro
403.01.04 | 450mm Ø | m | rate only |  | ro
| Total Carried to Summary |  |  | R

## Section 502
Item No | Description | Unit | Quantity | Rate | Amount
SERIES 5 | DRAINAGE AND EROSION
PROTECTION
Ref Dwgs: 1600073-08-81-C-301
Section 502 | Prefabricated Culverts,
Stormwater
502.01 | Backfilling with selected excavated
material compacted to -
Ref Dwgs: 7515-S205
502.01.01 | 90% of modified AASHTO density | m³ | 55
502.01.03 | 95% of modified AASHTO density | m³ | 125
502.02 | Supplying and laying of concrete
pipe culverts (Spigot and socket)
502.02.01 | Class B bedding / Class 100D
502.02.01.01 | 450mm Ø | m | 115
502.10 | Cast in situ concrete
Ref Dwgs: 1600073-08-81-C-310
502.10.03 | Inlet and outlet structures, catchpits,
manholes and junction boxes. Including
form work, reinforcing and surface finishes.
502.10.03.01 | Class 20/19 | m³ | 5
| Total Carried to Forward |  |  | R
502.10.02 | In invert slabs for portal or
rectangular culverts, including
formwork to provide Class F1 surface
finish and Class U2 surface finish
for unformed surfaces
ITEM | DESCRIPTION | UNIT | QTY | RATE | AMOUNT
502.10.02.01 | Class 25/19 | m³ | rate only |  | ro
502.10.03 | Inlet and outlet structures, catchpits,
manholes and junction boxes
complete
502.10.03.01 | Class 20/19 | m³ | 190
502.10.03.02 | Class 25/19 | m³ | rate only |  | ro
502.13 | Welded-steel fabric
502.13.01 | Reference 888 | kg | rate only |  | ro
502.13.02 | Reference 617 | kg | rate only |  | ro
502.13.03 | Reference 395 | kg | rate only |  | ro
502.14 | Reinforcement
502.14.01 | Mild steel
502.14.01.01 | 8mm dia. | t | rate only |  | ro
502.14.01.02 | 10mm dia. | t | rate only |  | ro
502.14.02 | High-yield-stress
502.14.02.01 | 8mm dia. | t | rate only |  | ro
502.14.02.02 | 10mm dia. | t | rate only |  | ro
502.14.02.03 | 12mm dia. | t | rate only |  | ro
| Total Brought Forward |  |  | R
502.16 | Manholes, catchpits, precast inlet and
outlet structures and junction boxes complete
502.16.01 | Manholes | No | 3
502.16.02 | Catchpits | No. | 1
502.16.03 | Precast Inlets and outlets | No. | rate only |  | ro
502.16.04 | Transitions | No. | 30
502.16.05 | Junction Boxes | No. | rate only |  | ro
502.17 | Brick work
502.17.01 | 115mm thick | m² | rate only |  | ro
502.17.02 | 230mm thick | m² | 737
502.17.03 | 345mm thick | m² | rate only |  | ro
502.18 | Plaster | m² | 700
502.19 | Benching | m² | 481
502.20 | Accessories
502.20.01 | Manhole covers including frames
502.20.01.02 | Combination precast concrete / cast
| iron frame and cover | no | 3
502.20.03 | Step Irons | no | 10
502.20.04.01 | Catchpit cover slabs Class 25/19 | no | 5
concrete
| Total Carried to Summary |  |  | R

## Section 504
Item No | Description | Unit | Quantity | Rate | Amount
SERIES 5 | DRAINAGE AND EROSION PROTECTION
Section 504 | Open Drains
Ref Dwgs: 1600073-08-81-C- 301-310
504.04 | Channels
504.04.01 | 300mm wide (top width) V-Drain.
(The tendered rate shall include full
compensation for procuring,furnishing and
installing the channel complete in all respects
including excavation where necessary by hand,
trimming the excavations and disposing of
excavation material as directed by the
| Engineer. | Lump Sum
| Total Carried to Summary |  |  | R

## Summary A
| BILL NO 2 - BULK EARTHWORKS SUMMARY | Page No |  | Amount
SERIES 1 | ANCILLARY WORK
101 | Site Clearing and Grubbing | -52-
SERIES 2 | EARTHWORKS
202 | Trench Excavation | -53-
203 | Mass Earth Works | -55-
SERIES 3 | SEWERS
Section 302 | Construction | -57-
Section 303 | Testing | -58-
SERIES 4 | WATER
Section 402 | Construction | -61-
Section 403 | Testing | -62-
SERIES 5 | DRAINAGE AND EROSION PROTECTION
502 | Prefabricated Culverts and stormwater | -64-
504 | Erosion Protection | -65-
| TOTAL CARRIED TO FINAL SUMMARY |  | R

## Series 07
Item No | Description | Unit | Quantity | Rate | Amount
BILL N0 3 - LATERAL SUPPORT
SERIES 7: STRUCTURES
SECTION PIC708: GROUND ANCHORS AND SHOTCRETE
PIC708.04: Ground Anchors
PIC708.04.01 | Moving to and setting up the equipment at each position for drilling the holes | number (No) | 2439
PIC708.04.02 | Drill holes with diameter of 115mm to the specified depths and inclinations of 10O below the horizontal
a | 0 - 6m | m | 15246
b | 6m to 9m | m | 6237
c | 9m to 12m | m | 3860
PIC708.04.03 | Water Tests | number (No) | 2439
PIC708.04.04 | Grouting and Re-drilling | m | 7603
PIC708.04.05 | Anchorages and Couplers
a | Bars with anchorage at Jacking End
i. | High Yield 25mm Bars x 12m - 220kN | No. | 1233
ii | High Yield 25mm Bars x 9m - 220kN | No. | 729
iii |  | No. | 437
iv | High Yield 25mm Bars x 4m - 220kN | No. | 40
b | Coupler at Jacking End
i. | High Yield 25mm Bars - 220kN | No. | 2439
PIC708.04.06 | Extra Over for Establishment on site for SDA Drilling Equipment | Lump Sum | 1
PIC708.04.07 | Extra Over for SDA Drill holes with diameter of 115mm to the specified depths and inclinations of 10O below the horizontal
i. | R25N Hollow Bar | m | 72
ii | R32S Hollow Bar | m | 72
PIC708.04.08 | Grouting of Anchors | m | 25343
| Total Carried to Forward |  |  | R
Item No | Description | Unit | Quantity | Rate | Amount
| Total Brought Forward |  |  | R
708.07: SHOTCRETE
PIC708.07.01 | Shotcrete of 200mm applied in three layers as shown on the drawings | m2 | 7900
703 | Steel Reinforcement for Structures
703.03 | Welded Steel Fabric
703.03.01 | In shotcrete walls both faces
703.03.01.01 | Mesh Ref. 395 | t | 63
703.04 | Reinforcement for gunite wall corners
703.04.02 | High yield steel
703.04.02.02 | Bars with a 10mm dia (Y10) | t | 1
PIC708.07.02 | Subsoil Drainage
i | Zipcore drain at 1.5m/2m centres | m | 6500
ii | 75mm uPVC outlets to drainage layer | m | 130
PIC708.07.03 | Monitoring | Lump Sum | 1
PIC708.07.04 | Finishing of shotcrete along brow of cut face | m | 530
| Total Carried to Summary |  |  | R

## Lateral support summary
| BILL NO 3 - LATERAL SUPPORT SUMMARY | Page No |  | Amount
SERIES 7 | STRUCTURES | -68-
| TOTAL CARRIED TO FINAL SUMMARY |  | R

## Final Summary
BILL NO | FINAL SUMMARY | Page No |  | Amount
1 | PRELIMINARY AND GENERAL | -51-
2 | BULK EATHWORKS | -66-
3 | LATERAL SUPPORT | -69-
SUB-TOTAL
Contingencies
| Allow a contingency amount at 5% of the contract amount to be used as directed by the Employer. | %
R
| ADD: VALUE ADDED TAX @15% |  | R
| TOTAL CARRIED TO FORM OF TENDER |  | R